## Agile Sprint Backlog
AGILE SPRINT BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE HOURS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #3 As a researcher, I want to create a questionnaire, so that I can collect data from users. | 5
Create a table of questionnaires in the database. | 1 | Andres | In progress | 8 | 6
Create front end with an option to create a questionnaire | 2 | Calum | Not started | 16 | 16
Create back end to store the created questions on the database | 2 | Rokas | Not started | 16 | 16
User Story #25 As a PR I want to have full access to my own experiments, so that I can fully analyse them. | 2
Create field on user's table inside the database to store the level of privileges I have | 1 | Andres | In progress | 8 | 6
Create a front end page where all experiments are displayed | 1 | Skye | Not started | 8 | 8
User story #12 As a researcher I want to be able to tick a box to state that an experiment has ethical approval, so that it is never started without approval. | 2
Front end for tick box | 1 | Skye | Not started | 8 | 8
Store status of ethical approval in the database | 1 | Calum | Not started | 8 | 8
User Story #29 As a lab manager I want to have access to all experiments in the whole lab so that I can overview all current projects | 3
Create a table in the database to store the projects that are being run | 1 | Jokubas | Not started | 8 | 8
Create a front end that will display the experiments | 1 | Skye | Not started | 8 | 8
Create back end that will take the information from the database and send it to the front end | 1 | Jokubas | Not started | 8 | 8
User Story #2 As a researcher I want to have a password protected account I can log into, so that access is restricted. | 5
Create a table in the database to store the user credentials | 2 | Andres | In progress | 16 | 12
Create a front end to ask for user credentials | 1 | Calum | In progress | 8 | 6
Create a back end that checks the info coming from the front end with the stored inside the database | 2 | Rokas | Not started | 16 | 16
User Story #39 As a researcher I want to add a new experiment, so that I can manage my study. | 3
Create a table of experiments in the database | 1 | Jokubas | Not started | 8 | 8
Create a front end to select a type of experiment | 1 | Skye | Not started | 8 | 8
Store the experiment in the database | 1 | Jokubas | Not started | 8 | 8
Testing | 6 | Emilija, Alina | Not started | 48 | 48
TOTAL ACTUAL | 26 |  |  | 208 | 198 | 0 | 0 | 0 | 0
ESTIMATED |  |  |  | 208 | 166.4 | 124.8 | 83.2 | 41.6 | 0
Status
[11 empty] | Not started | 13
[11 empty] | In progess | 4
[11 empty] | Completed | 0