## Agile Sprint Backlog
AGILE SPRINT BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User story #79 As a researcher I want to add general information to a questionnaire, so that I can inform participants about associated aspects. | 5
Create database entities to store general information within the questionnaire table | 1 | Andres/Jokubas | Not started | 10
Create front end with relevant fields to add general information | 2 | Alina/Emilija | Not started | 20
Create backend methods to receive and save general information | 2 | Rokas | Not started | 20
User story #4 As a researcher I want to add a new question to the questionnaire, so that I can get data from the participant. | 5
Create question table inside the database with the required fields from the example layout | 1 | Andres | Not started | 10
Create front end to add a new question (optionality, description, select the type, insert question title) | 2 | Emilija/Alina | In progress | 20
Routing to the correct question type modal/pop-up | 2 | Jokubas | Not started | 20
User story #82 As a researcher I want to add a System Usability Scale, so that I can ask participants to rate different statements. | 8
Create database entitiy to store a System Usability Scale question | 1 | Andres | Not started | 10
Create front end for modal (choose scale and statements) | 3 | Calum | Not started | 30
Create front end to display System Usability Scale (on the questionnaire) | 3 | Skye | Not started | 30
Create backend to save the question scale | 1 | Jokubas | Not started | 10
User story #81 As a researcher I want to add a multiple-choice question, so that I can ask participants to select a given answer. | 5
Create table field with a determined attribute range | 1 | Andres | Not started | 10
Create front end to display multiple choice question on the questionnaire | 1 | Skye | In progress | 10
Create front end for modal (choose options, choosing checkbox or radio) | 2 | Calum | Not started | 20
Create backend methods to receive and save questions | 1 | Rokas | Not started | 10
User story #80 As a researcher I want to add an open answer question, so that I can ask participants to write their own answer. | 3
Create database field to store a large amount of text | 1 | Jokubas/Andres | Not started | 10
Create front end to display open answer question on the questionnaire | 1 | Emilija | Not started | 10
Create backend methods to receive and save questions | 1 | Rokas | Not started | 10
Fix: As a researcher I want to be able to enter a code when asked if ethical approval was given, so that I can prove my research was checked. #87 | 2 | Rokas | Not started | 20
Testing | 5 | Alina, Emilija, Jokubas | In progress | 50
TOTAL ACTUAL | 33 |  |  | 330 | 0 | 0 | 0 | 0 | 0
ESTIMATED |  |  |  | 330 | 264 | 198 | 132 | 66 | 0
Status
[11 empty] | Not started | 16
[11 empty] | In progress | 3
[11 empty] | To test | 0
[11 empty] | Completed | 0