## Sheet1
ID | As a < type of user > | I want to < perform some task > | so that I can < achieve some goal > | Comment | Priority | MoSCoW | Test Proposition | Story Points | Sprint | Status
2 | Researcher | have a password protected account I can log into | ensure access is restricted. | account types: lab manager, principal researcher, co-researcher | High/ Medium | Must | • login for each user type • response to wrong login details, invalid input • database (data mapping, ACID, integrity) | 5 | 1 | In Progress
39 | Principal Researcher | add a new experiment | manage my study. | experiment types: questionnaire, video transcript, recording, etc. | High | Must | • add different types of experiments • check database entries | 3 | 1 | In Progress
3 | Researcher | create a questionnaire | collect data from users. | see example file: title, description, name, contact, etc. | High | Must | • create multiple with same name • distinguishable? • check database entries | 5 | 1 | In Progress
29 | Lab Manager | have access to all experiments in the whole lab | overview all current projects. |  | High/ Medium | Must | • access all available pages • check access to experiment assigned to other | 3 | 1 | In Progress
25 | Principal Researcher | have full access to my own experiments | fully analyse them. |  | High/ Medium | Must | • access own experiments • access denied everywhere else | 2 | 1 | In Progress
12 | Researcher | be able to tick a box to state that an experiment has ethical approval | never start an experiment without approval. |  | High/ Medium | Must | • only continue if box checked • compare before / after database entry | 2 | 1 | In Progress
4 | Researcher | add a new question to the questionnaire | get data from the participant. | choose type, choose title and description, choose if answer mandatory | High | Must | • database entries for different kinds • finished questionnaire complete? | 5 |  | To be started
| Researcher | add an open answer question | ask participants to write their own answers. |  |  |  | • enter any characters • text length? | ? |  | To be started
| Researcher | add a multiple choice question | ask participants to select a given answer. | add answer options |  |  | • add new answer option • remove/ edit answer | ? |  | To be started
| Researcher | add a System Usability Scale | ask participants to rate different statements. | https://www.researchgate.net/figure/The-System-Usability-Scale-SUS-questionnaire_fig6_271336759 |  |  | • edit answer range • add new statement | ? |  | To be started
34 | Participant | carry out questionnaires | contribute to the research. |  | High | Must | • access through link • answer questions • send off • answers recorded in DB | 5 |  | To be started
5 | Researcher | create a link to a questionnaire | participants get access. |  | High/ Medium | Must |  | 5 |  | To be started
42 | Researcher | upload a video file | analyse the content. | upload as mp4s, max 125MB | Medium | Should |  | ? |  | To be started
13 | Researcher | be able to easily generate a transcript from video interviews | analyse the videos more easily. |  | Medium | Should |  | 5 |  | To be started
7 | Researcher | be able to export data from a questionnaire as a CSV file | analyse it later. |  | High | Must | • check completeness • different file format | 5 |  | To be started
9 | Researcher | know the number of people that participated in a questionnaire | evaluate response numbers. |  | Medium/ Low | Should |  | 2 |  | To be started
10 | Researcher | see the distribution of answers for each question | quickly judge responses. |  | Medium/ Low | Should |  | 3 |  | To be started
31 | Lab Manager | add new users | ensure new people can work on projects. |  | High/ Medium | Must |  | 3 |  | To be started
| Principal Researcher | add new co-researchers to my experiments | collaborate with other scientists.
| Principal Researcher | delete excisting co-researchers from my experiments | restrict access to my research.
28 | Co-Researcher | have access to experiments assigned to me by a PR | ensure the protection of sensible data. |  | High/ Medium | Must |  | 2 |  | To be started
32 | Lab Manager | be able to reset passwords of users | ensure all users have access. |  | Medium | Must |  | 3 |  | To be started
33 | Lab Manager | be able to remove users | ensure users that leave the facility lose their online access as well. |  | Medium | Must |  | 2 |  | To be started
38 | User | have secure login procedures | the data is protected. |  | High | Must |  | 8 |  | To be started
14 | Researcher | be able to select a quote from the transcript | further analyse it. |  | Medium | Should |  | 5 |  | To be started
19 | Epic: Researcher | analyse all of my data on one system | manage the process of the study more easily. |  | Medium | Should |  | ? |  | To be started
1 | Epic: Researcher | carry out a variety of research studies within the HCC group | analyse the results. |  | Medium/ Low | Should |  | 8 |  | To be started
23 | Researcher | take notes on certain moments from research footage | compare how different participants behave after receiving the same input. |  | Medium | Should |  | 5 |  | To be started
30 | Lab Manager | have a list of the current projects and the assigned researchers | stay up to date on all experiments. |  | Low | Should |  | 3 |  | To be started
8 | Epic: Researcher | visualize data | see a rough picture of how things are looking. |  | Medium | Could |  | 13 |  | To be started
15 | Researcher | attach one or more different tags (themes) to a selected quote | give a brief summary of what they mean. | 1 quote can have many themes. 1 theme can have many quotes. | Low | Could |  | 3 |  | To be started
16 | Researcher | be able to create new themes | more accurately describe a quote. |  | Low | Could |  | 3 |  | To be started
21 | Researcher | ask the participants questions about their experience with the browser task afterwards | also get input about user experience. |  | Low | Could |  | 3 |  | To be started
18 | Researcher | generate relationships between quotes by grouping together 3 or 4 similar ones | create ‘super’ themes. |  | Low | Could |  | 5 |  | To be started
17 | Researcher | condense themes to a reasonable level | similar ones are coherent. |  | Low | Could |  | ? |  | To be started
22 | Researcher | make sure all input videos from different cameras are paused at the same moment. | synchronize the videos when playing and compare them. |  | Medium | Could |  | 8 |  | To be started
24 | Researcher | have a timestamp on all notes with the correct, synchronized video times | keep notes that are consistent across multiple videos. |  | Low | Could |  | ? |  | To be started
11 | Epic: Researcher | have an easier process for submitting ethics forms | carry out data collection with less delay. | https://www.dundee.ac.uk/research/governance-policy/ethicsprocedures/ethics/applicationprocedure/ | Low | Won't |  | ? |  | To be started
20 | Researcher | record a participant and their screen while they carry out a task in a web browser | analyse their behaviour later. | not done very often | Medium | Could |  | 8 |  | To be started
6 | Researcher | send a questionnaire (link) to people | get their answers. |  | Low | Could |  | 8 |  | To be started