## Sheet1
DATE | TEST # | TASK DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASSED | TESTED BY | TESTER COMMENTS
2021-01-28 | 1 | Login form responsiveness | repsonds to screen size and stays usable | responsiveness changes sizes of boxes | Yes | Alina
2021-01-28 | 2 | Logging in with incorrect details | should not be able to log in, error message | error message received | Yes | Alina
2021-01-28 | 3 | Logging in with correct details | login successful, directed to home screen | login successful, dircted to experiment overview page | Yes | Alina
2021-01-28 | 4 | Logging in as lab manager | privileges level 3 | logged in with correct privileges | Yes | Alina
2021-01-28 | 5 | Logging in as principal researcher | privileges level 2 | logged in with correct privileges | Yes | Alina
2021-01-28 | 6 | Logging in as co-researcher | privileges level 1 | logged in with correct privileges | Yes | Alina
2021-01-28 | 7 | Add a new experiment | prompted to enter details of experiment | asked to select title, description & type of experiment | Yes | Alina
2021-01-28 | 8 | Create experiment form responsiveness | repsonds to screen size and stays usable | text fileds dissapear behind each other | No | Emilija | add responsiveness for labels
2021-01-28 | 9 | Create experiment with all details | directed to new experiment page | success message, but no redirection | No | Alina | after submitting should be redirected to new poge
2021-01-28 | 10 | Create experiment with details missing | prompted to enter missing details | unexected error | No | Alina | details on which info is missing
2021-01-28 | 11 | Experiment overview after adding new one | new experiment added to list | list has new item with experiment | Yes | Alina
2021-01-28 | 12 | Add a new questionnaire | select title, description, name, contact info, ethical approval tickbox
2021-01-28 | 13 | Create a new questionnaire with ethical approval | directed to adding questions
2021-01-28 | 14 | Create a new questionnaire without ethical approval | warning to get ethical approval first
2021-01-28 | 15 | Create a new questionnaire with missing information | prompted to enter missing details
|  | Experiment list as lab manager | show all current experiments, from all researchers
|  | Experiment list as PR | show only own experiments
|  | Logging out | directed to login page, success message and no more access to page