## Sheet1
DATE | TEST # | TASK DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASSED | TESTER COMMENTS
2021-02-03 | 1 | tick ethical approval box and enter code | able to continue to next page, code is added to a databse | button add questionnaire is active, user can redirect to another page | Yes
2021-02-03 | 2 | submit ethical approval without code | error message is displayed | error message to enter code is displayed | Yes
2021-02-03 | 3 | remove ethics approval tick | after removal continuing impossible | button add questionnaire is not active, impossible to proceed | Yes
2021-02-04 | 4 | look up experiment page with a questionnaire | option to remove ethical approval, name of questionnaire and options to view, create link or delete questionnaire | option to remove ethical approval, questionnaire and options displayed | Yes
2021-02-04 | 5 | look up experiment page without a questionnaire | option to get/ remove ethical approval, add questionnaire button | option to get/ remove ethical approval, add questionnaire button | Yes
2021-02-02 | 6 | add info about questionnaire correctly (title, description, researchers, contact info, agreement,...) | directs to a questionnaire page, correct info displayed on top | directs to a questionnaire page, general information is displayed on top | Yes
2021-02-04 | 7 | add info about questionnaire with empty fields | error message, prompted to enter missing info | message displayed, user is not redirected to questionnaire | Yes
2021-02-04 | 8 | add question correctly (type, title, optionality, description) | question appears on the page with all associated data displayed | Questions added to DB, but not retrieved from database | No
2021-02-02 | 9 | add mandatory question | displayed with mandatory marking | Front-end can show mandatory or not with placeholder data. | No | Should test once backend done.
2021-02-02 | 10 | add not mandatory question | displayed without mandatory marking | Front-end can show mandatory or not with placeholder data. | No | Should test once backend done.
2021-02-02 | 11 | add question with description | question appears on the page with description | correctly added to DB, no frontend integration with database yet | No | only integration missing
2021-02-02 | 12 | add question without description | question appears on the page without description | correctly added to DB, no frontend integration with database yet | No | only integration missing
2021-02-02 | 13 | add open answer question | question and empty text field appear on questionnaire | Front-end appears with placeholder data for now. | No
2021-02-02 | 14 | add MC question with one possible answer (radio buttons) | question apprears with radio buttons for answers, only one answer can be selected | Front-end appears with placeholder data for now. | No
2021-02-02 | 15 | add MC question with multiple possible answers (checkboxes) | question apprears with checkboxes for answers, 0+ can be selected | Front-end appears with placeholder data for now. | No
2021-02-02 | 16 | add question with system usability scale | question appears with a defined scale options | Front-end appears with placeholder data for now. | No
2021-02-04 | 17 | select open answer question | a button to add a question is active (if all details are filled in) | button to add question becomes enabled | Yes
2021-02-04 | 18 | select MC question with one possible answer (radio buttons) | a box to enter answers options is displayed | a box to enter options is displayed | Yes
2021-02-04 | 19 | select MC question with multiple possible answers (checkboxes) | a box to enter answers options is displayed | a box to enter options is displayed | Yes
2021-02-04 | 20 | select question with system usability scale | a box to select the scale range is displayed | a box to select the scale range is displayed | Yes
| 21 | enter range 10 for SUS | SUS displayed with 10 answer options
| 22 | enter range 5 for SUS | SUS displayed with 5 answer options
2021-02-04 | 23 | add question with missing mandatory fields (title, optionality, type, answers) | error message, prompted to enter missing info | error message to enter missing details is displayed | Yes
2021-02-04 | 24 | click finish questionnaire | success message, questionnaire is saved |  | No
2021-02-04 | 25 | look up finished questionnaire | a title and buttons (delete/send link/view) are displayed on the experiment page, create experiment is gone |  | Yes