## Agile Sprint Backlog
AGILE SPRINT BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User story #79 As a researcher I want to add general information to a questionnaire, so that I can inform participants about associated aspects. | 5
Create database entities to store general information within the questionnaire table | 1 | Andres/Jokubas | Completed | 10 | 6 | 2 | 2 | 0
Create front end with relevant fields to add general information | 2 | Alina | Completed | 20 | 20 | 5 | 2 | 0
Create backend methods to receive and save general information | 2 | Rokas | Completed | 20 | 20 | 18 | 10 | 0
User story #4 As a researcher I want to add a new question to the questionnaire, so that I can get data from the participant. | 5
Create question table inside the database with the required fields from the example layout | 1 | Andres | To test | 10 | 8 | 4 | 2 | 0
Create front end to add a new question (optionality, description, select the type, insert question title) | 2 | Emilija | To test | 20 | 16 | 6 | 0 | 0
Displaying the correct box to enter answer options or scale if needed | 1 | Jokubas | To test | 10 | 9 | 8 | 8 | 0
Create backend methods to receive and save information about the question | 1 | Jokubas | To test | 10 | 10 | 6 | 2 | 0
User story #82 As a researcher I want to add a System Usability Scale, so that I can ask participants to rate different statements. | 8
Create database entitiy to store a System Usability Scale question | 1 | Andres | Completed | 10 | 8 | 4 | 2 | 0
Create front end to choose scale | 3 | Calum | To test | 30 | 30 | 25 | 5 | 0
Create front end to display System Usability Scale on the questionnaire | 3 | Skye | To test | 30 | 30 | 30 | 10 | 5
Create backend to save the question scale | 1 | Jokubas | To test | 10 | 10 | 10 | 10 | 0
User story #81 As a researcher I want to add multiple-choice answers, so that I can ask participants to select a given answer. | 5
Create table to store the possible answers from the multiple choice question | 1 | Andres | Completed | 10 | 8 | 8 | 4 | 0
Create front end to display multiple choice question on the questionnaire | 2 | Skye | To test | 20 | 15 | 0 | 0 | 0
Create front end to add answer options | 1 | Calum | To test | 10 | 5 | 3 | 1 | 0
Create backend methods to receive and save question options | 1 | Rokas | To test | 10 | 10 | 10 | 10 | 8
User story #80 As a researcher I want to add an open answer, so that I can ask participants to write their own answer. | 1
Create front end to display open answer question on the questionnaire | 1 | Skye | To test | 10 | 5 | 0 | 0 | 0
User story #106 As a researcher I want to see that the questionnaire was created, so that I can check that it was added correctly. | 2 | Emilija, Jokubas | To test | 20 | 20 | 20 | 10 | 5
Fix: As a researcher I want to be able to enter a code when asked if ethical approval was given, so that I can prove my research was checked. #87 | 2 | Rokas | Completed | 20 | 10 | 2 | 0 | 0
User story #109 As a researcher I want to review an existing questionnaire, so that I can check all questions are correct. | 2 | Jokubas | To test | 20 | 20 | 20 | 20 | 5
Testing | 5 | Alina, Emilija, Jokubas | In progress | 50 | 40 | 30 | 20 | 15
TOTAL ACTUAL | 35 |  |  | 350 | 300 | 211 | 118 | 38 | 0
ESTIMATED |  |  |  | 350 | 280 | 210 | 140 | 70 | 0
Status
[11 empty] | Not started | 0
[11 empty] | In progress | 1
[11 empty] | To test | 13
[11 empty] | Completed | 6