## Sheet1
ID | Priority | As a < type of user > | I want to < perform some task > | so that I can < achieve some goal > | Comment | Sprint | Status
3 | High | Researcher | create a questionnaire | collect data from users.
4 | High | Researcher | add a new question to the questionnaire | get data from the participant. | Open question, multiple choice (yes-no-maybe / one or multiple possible answers), System Usability Scale https://www.researchgate.net/figure/The-System-Usability-Scale-SUS-questionnaire_fig6_271336759)
34 | High | Participant | carry out questionnaires | contribute to the research.
7 | High | Researcher | be able to export data from a questionnaire as a CSV file | analyse it later.
38 | High | User | have secure login procedures | the data is protected.
2 | High/ Medium | Researcher | have a password protected account I can log into | ensure my research is safe and access is restricted.
12 | High/ Medium | Researcher | be able to tick a box to state that an experiment has ethical approval | never start an experiment without approval.
5 | High/ Medium | Researcher | create a link to a questionnaire | participants get access.
36 | High/ Medium | User | see the university branding | identify the website’s origin.
25 | High/ Medium | Principal Researcher | have full access to my own experiments | fully analyse them.
31 | High/ Medium | Lab Manager | be able to add new users | ensure new people can work on projects.
29 | High/ Medium | Lab Manager | have access to all experiments in the whole lab | overview all current projects.
26 | High/ Medium | Principal Researcher | have a list of all my Co-researchers | select different people for different parts of the project.
27 | High/ Medium | Principal Researcher | select the experiments each of my CoRs has access to | restrict their access to approved experiments.
28 | High/ Medium | Co-Researcher | have only access to parts my PR has selected | ensure the protection of sensible data.
14 | Medium | Researcher | be able to select a quote from the transcript | further analyse it.
13 | Medium | Researcher | be able to easily generate a transcript from video interviews | analyse the videos more easily.
23 | Medium | Researcher | take notes on certain moments from research footage | compare how different participants behave after receiving the same input.
32 | Medium | Lab Manager | be able to reset passwords of users | ensure all users have access.
33 | Medium | Lab Manager | be able to remove users | ensure users that leave the facility lose their online access as well.
8 | Medium | Epic: Researcher | visualize data | see a rough picture of how things are looking.
22 | Medium | Researcher | make sure all input videos from different cameras are paused at the same moment in time | synchronize the videos when playing and compare them.
20 | Medium | Researcher | record a participant and their screen while they carry out a task in a web browser | analyse their behaviour later.
19 | Medium | Epic: Researcher | analyse all of my data on one system | manage the process of the study more easily.
9 | Medium/ Low | Researcher | know the number of people that participated in a questionnaire | evaluate response numbers.
10 | Medium/ Low | Researcher | see the distribution of answers for each question | quickly judge responses.
1 | Medium/ Low | Epic: Researcher | carry out a variety of research studies within the HCC group | analyse the results.
37 | Medium/ Low | User | have a user friendly product | easily use it. | Design, accessibility, clearness,
35 | Medium/ Low | Participant | have the product follow the disability-access guidelines | use it with no problems even if I have special needs. | Text font and size
30 | Low | Lab Manager | have a list of the current projects and the assigned researchers | stay up to date on all experiments.
15 | Low | Researcher | attach one or more different tags (themes) to a selected quote | give a brief summary of what they mean. | 1 quote can have many themes. 1 theme can have many quotes.
16 | Low | Researcher | be able to create new themes | more accurately describe a quote.
21 | Low | Researcher | ask the participants questions about their experience with the browser task afterwards | also get input about user experience.
18 | Low | Researcher | generate relationships between quotes by grouping together 3 or 4 similar ones | create ‘super’ themes.
17 | Low | Researcher | condense themes to a reasonable level | similar ones are coherent.
6 | Low | Researcher | send a questionnaire (link) to people | get their answers.
24 | Low | Researcher | have a timestamp on all notes with the correct, synchronized video times | keep notes that are consistent across multiple videos.
11 | Low | Epic: Researcher | have an easier process for submitting ethics forms | carry out data collection with less delay. | https://www.dundee.ac.uk/research/governance-policy/ethicsprocedures/ethics/applicationprocedure/