## Sheet1
ID | As a < type of user > | I want to < perform some task > | so that I can < achieve some goal > | Comment | Priority | MoSCoW | Test Proposition | Story Points | Sprint | Status
2 | Researcher | have a password protected account I can log into | ensure my research is safe and access is restricted. |  | High/ Medium | Must |  | 5 | 1 | In Progress
39 | Researcher | add a new experiment | manage my study. |  | High | Must |  | 3 | 1 | In Progress
3 | Researcher | create a questionnaire | collect data from users. |  | High | Must |  | 5 | 1 | In Progress
29 | Lab Manager | have access to all experiments in the whole lab | overview all current projects. |  | High/ Medium | Must |  | 3 | 1 | In Progress
25 | Principal Researcher | have full access to my own experiments | fully analyse them. |  | High/ Medium | Must |  | 2 | 1 | In Progress
12 | Researcher | be able to tick a box to state that an experiment has ethical approval | never start an experiment without approval. |  | High/ Medium | Must |  | 2 | 1 | In Progress
4 | Researcher | add a new question to the questionnaire | get data from the participant. | Open question, multiple choice (yes-no-maybe / one or multiple possible answers), System Usability Scale https://www.researchgate.net/figure/The-System-Usability-Scale-SUS-questionnaire_fig6_271336759) | High | Must |  | 5
34 | Participant | carry out questionnaires | contribute to the research. |  | High | Must |  | 5
7 | Researcher | be able to export data from a questionnaire as a CSV file | analyse it later. |  | High | Must |  | 5
38 | User | have secure login procedures | the data is protected. |  | High | Must |  | 8
5 | Researcher | create a link to a questionnaire | participants get access. |  | High/ Medium | Must |  | 5
31 | Lab Manager | be able to add new users | ensure new people can work on projects. |  | High/ Medium | Must |  | 3
26 | Principal Researcher | have a list of all my Co-researchers | select different people for different parts of the project. |  | High/ Medium | Must |  | 2
27 | Principal Researcher | select the experiments each of my CoRs has access to | restrict their access to approved experiments. |  | High/ Medium | Must |  | 3
28 | Co-Researcher | have only access to parts my PR has selected | ensure the protection of sensible data. |  | High/ Medium | Must |  | 2
32 | Lab Manager | be able to reset passwords of users | ensure all users have access. |  | Medium | Must |  | 3
33 | Lab Manager | be able to remove users | ensure users that leave the facility lose their online access as well. |  | Medium | Must |  | 2
9 | Researcher | know the number of people that participated in a questionnaire | evaluate response numbers. |  | Medium/ Low | Should |  | 2
10 | Researcher | see the distribution of answers for each question | quickly judge responses. |  | Medium/ Low | Should |  | 3
13 | Researcher | be able to easily generate a transcript from video interviews | analyse the videos more easily. |  | Medium | Should |  | 5
14 | Researcher | be able to select a quote from the transcript | further analyse it. |  | Medium | Should |  | 5
19 | Epic: Researcher | analyse all of my data on one system | manage the process of the study more easily. |  | Medium | Should |  | ?
1 | Epic: Researcher | carry out a variety of research studies within the HCC group | analyse the results. |  | Medium/ Low | Should |  | 8
23 | Researcher | take notes on certain moments from research footage | compare how different participants behave after receiving the same input. |  | Medium | Should |  | 5
30 | Lab Manager | have a list of the current projects and the assigned researchers | stay up to date on all experiments. |  | Low | Should |  | 3
8 | Epic: Researcher | visualize data | see a rough picture of how things are looking. |  | Medium | Could |  | 13
15 | Researcher | attach one or more different tags (themes) to a selected quote | give a brief summary of what they mean. | 1 quote can have many themes. 1 theme can have many quotes. | Low | Could |  | 3
16 | Researcher | be able to create new themes | more accurately describe a quote. |  | Low | Could |  | 3
21 | Researcher | ask the participants questions about their experience with the browser task afterwards | also get input about user experience. |  | Low | Could |  | 3
18 | Researcher | generate relationships between quotes by grouping together 3 or 4 similar ones | create ‘super’ themes. |  | Low | Could |  | 5
17 | Researcher | condense themes to a reasonable level | similar ones are coherent. |  | Low | Could |  | ?
22 | Researcher | make sure all input videos from different cameras are paused at the same moment. | synchronize the videos when playing and compare them. |  | Medium | Could |  | 8
24 | Researcher | have a timestamp on all notes with the correct, synchronized video times | keep notes that are consistent across multiple videos. |  | Low | Could |  | ?
11 | Epic: Researcher | have an easier process for submitting ethics forms | carry out data collection with less delay. | https://www.dundee.ac.uk/research/governance-policy/ethicsprocedures/ethics/applicationprocedure/ | Low | Won't |  | ?
20 | Researcher | record a participant and their screen while they carry out a task in a web browser | analyse their behaviour later. | not done very often | Medium | Could |  | 8
6 | Researcher | send a questionnaire (link) to people | get their answers. |  | Low | Could |  | 8