## Agile Sprint Backlog
AGILE SPRINT BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE HOURS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #3 As a researcher, I want to create a questionnaire, so that I can collect data from users. | 5
Create a table of questionnaires in the database. | 1 | Andres | In progress | 8 | 6 | 4 | 2
Create front end with an option to create a questionnaire | 2 | Calum | In progress | 16 | 16 | 14 | 12
Create back end to store the created questions on the database | 2 | Rokas | In progress | 16 | 16 | 16 | 12
User Story #25 As a PR I want to have full access to my own experiments, so that I can fully analyse them. | 2
Create field on user's table inside the database to store the level of privileges I have | 1 | Andres | To test | 8 | 6 | 4 | 2
Create a front end page where all experiments are displayed | 1 | Skye | In progress | 8 | 6 | 4 | 2
User story #12 As a researcher I want to be able to tick a box to state that an experiment has ethical approval, so that it is never started without approval. | 2
Front end for tick box | 1 | Skye | To test | 8 | 8 | 8 | 2
Store status of ethical approval in the database | 1 | Calum | Not started | 8 | 8 | 8 | 8
User Story #29 As a lab manager I want to have access to all experiments in the whole lab so that I can overview all current projects | 3
Create a table in the database to store the projects that are being run | 1 | Jokubas | In progress | 8 | 8 | 2 | 1
Create a front end that will display the experiments | 1 | Skye | In progress | 8 | 6 | 4 | 2
Create back end that will take the information from the database and send it to the front end | 1 | Jokubas | In progress | 8 | 8 | 2 | 1
User Story #2 As a researcher I want to have a password protected account I can log into, so that access is restricted. | 5
Create a table in the database to store the user credentials | 2 | Andres | To test | 16 | 12 | 8 | 4
Create a front end to ask for user credentials | 1 | Calum | In progress | 8 | 6 | 3 | 2
Create a back end that checks the info coming from the front end with the stored inside the database | 2 | Rokas | In progress | 16 | 12 | 6 | 2
User Story #39 As a researcher I want to add a new experiment, so that I can manage my study. | 3
Integrate frontend with backend | 1 | Jokubas | To test | 8 | 6 | 4 | 2
Create a front end to create a new experiment | 1 | Skye | To test | 8 | 8 | 4 | 2
Store the experiment in the database | 1 | Jokubas | To test | 8 | 2 | 2 | 2
Testing | 6 | Emilija, Alina | In progress | 48 | 48 | 38 | 28
Create a website header | 2 | Emilija | In progress | 16 | 16 | 16 | 8
TOTAL ACTUAL | 28 |  |  | 224 | 198 | 147 | 94 | 0 | 0
ESTIMATED |  |  |  | 224 | 179.2 | 134.4 | 89.6 | 44.8 | 0
Status
[11 empty] | Not started | 1
[11 empty] | In progress | 11
[11 empty] | To test | 6
[11 empty] | Completed | 0